## Admin
Sr . No | Module | Sub-module | Defect | developer | tester
1 | login screen | username- enter and valid for both | replace msg "Please enter email ID." to Please enter username." and for valid email "Please enter valid email id." |  | 43445
2 | login screen |  | Remember Me - make the "Me" m small |  | 43445
3 | forgot password |  | without input clicked on reset password it is redirected to login page and error msg seen as "We got wrong response to proceed your request." -- give jquery validation as "Please enter email id. " |  | 43445
4 | forgot password |  | for invalid give validation msg as "Please enter valid email id." |  | 43445
5 | admin |  | add new module as "Dashboard" and after loggedin it should get redirected to dashboard or after login redirect it to banner page |  | 43445
6 | admin- header |  | image beside profile is not seen as the logo is in black color |  | not an issue
7 | admin- organization master |  | the note in red color change the color and size | design | give space between label name and note |  | done
color: #606060;font-size: 12px;
8 | admin- organization master | mobile no field | place holder mobile no - give dot after no. |  | 43445
9 | admin- organization master | maps url | if wrong entered then in front 404 error seen -give validation msg |  | 43445
10 | admin- organization master | linkedin field | linkedin field in organization master is not reflected in front follow us |  | for inkedin google icon given
11 | admin- organization master | social links | links if not inserted in organization master field then dont show in front |  | even then hide the follows on heading if no link input
12 | admin - settings |  | the background block for settings should be small from bottom | design | 43445
13 | admin - settings | cancel button | for cancel button 404 error |  | 43445
14 | admin - footer | where the copyright is | on click of Studio Interiors and Mplussoft it is changed to white color which is not visible | design | 43445
15 | admin - footer | where the copyright is | on click of Studio Interiors redirect to website front link |  | on click of Studio Interiors the link should get open in new tab
16 | admin- cms | banner list table | if no banner in table then msg "No records found in table." is seen but not in table i.e. The table is not seen | design | 43445
17 | admin- cms | banner | there should be space between default image and choose file | design | 43445
18 | admin- cms | table | the image visible should be in small size | design | 43445
19 | admin- cms | table | adjust the action buttons acording to space | design | 43445
20 | admin- cms - banner | add | success msg give as " Success! Banner added successfully. " |  | 43445
21 | admin- cms - banner |  | make the Delete - D small in "Do you really want to Delete this banner?" |  | 43445
22 | admin- cms - banner | for delete | delete success msg given as " Success! Banner has been updated successfully. ". Replace to " Success! Banner deleted successfully. " |  | 43445
23 | admin- cms - banner | image name | give limit of 30 characters.. "Maximum length is 30 characters." |  | 43445
24 | admin- cms - banner | title name | give limit of 150 characters.. "Maximum length is 150 characters." |  | 43445
25 | admin- cms - banner | active/inactive | Do you really want to Inactive this staff? - replace with Do you really want to Inactive this banner ? |  | 43445
26 | admin- cms - All Pages |  | page heading given as "Content Management System" -replace as "All Pages"
27 | admin- cms - All Pages |  | the theme color is blue i.e. Different from other pages | design | 43445
28 | admin- cms - About us | drawer | make About us - u in capital |  | 43445
29 | admin- cms - About us | fields design | the fields design and alignment is not proper | design | 43445
30 | admin- services |  | change the color of add services and edit button | design | 43445
31 | admin- services |  | change the spelling "Add servicess" to "Add Services' |  | 43445
32 | admin- services | table | the table heading keep center or left align ..either of one | design
33 | admin- services | add and edit page and validation msg | make the S capital of all services word on add/edit page and remove s from services |  | not done | done
34 | service | back button | design not proper | design | 43445
35 | admin- services | add and edit | the default image is not set | design | 43445
36 | admin- services | add,update,delete | in the success msg make the services S capital |  | 43445
37 | admin- services | add and edit | the meta keyword work pending |  | 43445
38 | admin- services | status | why the status option is given through add page and not in table ? |  | no need
39 | admin-blogs |  | change the color of add services and edit button | design | 43445
40 | admin-blogs | table | the table heading keep center or left align ..either of one | design
41 | admin-blogs | add and edit | make the content field mandatory |  | 43445
42 | admin-blogs | add and edit | the meta keyword work pending |  | 43445
43 | admin - gallery | upload photo | the default image not set | design | 43445
44 | admin - gallery | upload photo | multiple photo is selected but after submit only 1 image is uploaded | design | is it possible for multiple upload here |  | No
45 | admin - gallery | upload photo | click on upload button where image was not selected and just refreshed and continued the before uploaded image is again getting uploaded |  | not an issue
46 | admin - gallery | upload photo | without select if clicked on upload button and then select and click then requires double click then it is uploaded
47 | admin - gallery | delete button | give tooltip for delete button as "Delete" |  |  |  | Done
48 | admin - gallery | delete button | Do you really want to delete this record? - replace with "Do you really want to delete this photo ? |  | 43445
49 | admin - gallery | delete button | clicked on delete button , the popup comes but the delete icon below photo is not visible and even if cancel then also gone |  | 43445
50 | admin - testimonial | table | the table heading keep center or left align ..either of one | design
51 | admin - testimonial | add/edit | the word "testimonial" in add/edit page - make the T capital there |  | 43445
52 | admin - testimonial | add/edit | the back button design and theme color and even overall design | design | 43445
53 | admin - testimonial | add/edit | the default image not set | design | 43445
54 | admin - testimonial | success msg | the word "testimonial" - make the T capital there |  | 43445
43445
55 | cms | about us | the meta description is not added . |  | 43445
56 | admin- services | add | bydefault unpublished status y shown ? |  | 43445
57 | admin - testimonial |  | while add/edit if unpublished status selected and again view then it is not seen |  | 43445

## Front
Sr . No | Module | Sub-module | Defect | developer | tester
1 | front - banner |  | if only one banner is added then no need of showing the arrows. | design | 43445
2 | front - banner | slider dot | if 2 banner added then in front 3 dots seen and if more then 3 added then also 3 dots seen | design | 43445
3 | front - home -about us |  | content is hlf cut according to limit given so atleast need to show ..... Or read more option there |  | 43445
4 | front - home -about us-below |  | Why Choose Us - development work pending
5 | front - home -about us | view- advantage | development work pending
6 | front- services | heading name | if while add service name entered in small then in front side show 1st letter capital on services page and even in footer |  | 43445
7 | front- home -services |  | show 4 line and then ..... I.e. The length of block should be fixed - same |  | 43445 | still if heading big its coming down
8 | front- home -services | home and view service | what will be the showing seq.. On home new added is seen 1st and after view it is seen last | design
9 | front-home-Concept Based Design |  | development work pending
10 | front - blogs | home and view service | what will be the showing seq.. On home new added is seen 1st and after view it is seen last | design
11 | front - home -blogs |  | The length of block should be fixed - same - its bcoz of image size the length is getting increase | design | if name increase then the date is moving downwards
12 | front - blogs view | sharing option | development work pending
13 | front - blogs view | content | in the content space added between the paragraph but on front space is not taken |  | design |  | done
14 | front - blogs view | image | the image is half cut |  | 43445
15 | front - blogs list |  | the 3 rd added blog is not coming according to seq i.e. 4 blog is coming below 3 blog and blank below 1 and 2 blog | design | 43445
16 | front - gallery |  | how the banner image is changed and even how will be the seq for showing in front | design | 43445
17 | front - testimonial |  | if no testimonial available then dont show the section of testimonial in front home page |  | 43445
18 | front - testimonial |  | more content inserted then only half is seen and even no other page to view full |  | where u will see if content is more |  |  | ther should be character limit n no other view page
19 | front - testimonial |  | length should of fixed size |  | 43445
20 | front - testimonial |  | the image is not seen in circle | design | 43445
21 | front - contact us |  | contact info and leave a message block in not proper alignment | design | 43445
22 | front - contact us | leave a msg | the validation msg alignment not proper |  | design
23 | front - contact us | leave a msg | give validation msg to message as " Please enter message." |  | 43445
24 | front - contact us | leave a msg | the mail work pending
25 | front - contact us | leave a msg | give sucess msg after mail "Thank you for contacting us. We will get back to you soon." |  | 43445 | it is scrolling up after submit. If possible dont scroll
43445
26 | about us page |  | the content every word is starting with capital letter | design | 43445
27 | front- home -services |  | the line below heading - check the spelling of Livspace is it correct | design |  |  | correct
28 | front- home -services |  | on view of particular service from home it should go to the view page of that service |  | 43445
29 | services | 1st page | shown there 3-4 lines and then when clicked on read more - all data should be seen |  | 43445
30 | services | 2nd page - viewed | if less content then the space req below image | design |  |  | done
31 | front - blogs view | sharing option | if name is increase then the social media icons are also shifted below | design |  |  | done