## Admin
Sr. No. | Date | Module | Sub Module | Defect Description | Developer's Status | Tester's Status | Developer's Status 2 | Version
1 | 2019-02-06 | Vendor List |  | Should be in decending order | 2019-11-02
2 |  | Customer | View | Design improper | 12/2/2019 (design issue)
3 |  | Favicon |  | Favicon missing | 2019-11-02
4 |  | Products | Add product list | Edit>> click on cancel button>> not working edit functionality | its working |  | its working | 1
5 |  | Vendor | Vendor list>>View | Logo and vendor person name below it improper spacing. | 12/2/2019 (design issue)
6 |  | Vendor | Menu>> Add menu | Need image preview. | 12/2/2019 (design issue)
7 |  | Vendor | Ratings>> View | Ratings box has to be large as space at the right side is looking improper. | 2019-11-02
8 |  | Vendor | View | Large address overlaps. | 12/2/2019 (design issue)
9 |  | Vendor | View>> Menu>> Menu List>> Edit | Check on packetrs>> Insert amount>> Submit == Error | 2019-11-02
10 |  | Vendor |  | Need delete and edit button for special 'speciality'. | 2019-11-02
11 |  | Vendor | View>> Speciality | Speciality>> button name has to be 'Add New Speciality' also button has to be out of the speciality test box. | 2019-11-02 | Remove little space below the button
12 |  | Vendor | View>> Add Menu>> | Error while Continuously adding menus. | 2019-11-02
13 |  | Vendor | Add menu | Seller cost text box icon inside is missing. | 2019-11-02
14 |  | Organisation Master |  | Fb and google link box improper. | 2019-11-02 |  | not an issue | 1
15 |  | Organisation Master |  | Link box for Instagram is missing. | 2019-11-02
16 |  | Vendor | Add speciality | Should be ' Description' instead of 'Textarea' | 2019-11-02 | Recorrect it ( ' ) remove | 19/2/2019 | 1
17 | 2019-02-09 | Advertisement |  | Space between advertisement logo and text. | 19/2/2019
18 | 2019-02-11 | Sin In | Log in >> Logout >>Login again. | Previously loged in member details are saved.
19 |  | Customer | Customer List | Delete Customer >> Error! | 19/2/2019
20 |  | Customer | Disable any customer | Disabled customer is able to make transactions. | 19/2/2019
21 |  | Vendor | Add Menu | Cost field able to accept characters also. | 20/2/2019
22 |  | Vendor | View>> Menu List | Scroll bar at the bottom should not be at the bottomof the list but ath the bottom of the computer screen ( Lot of difficulties in scrolling right ,edit and deleting) | not mandatory
23 |  | Update Profile | Add new address | Clicking somewhere elso on screen making pop disappear while filling up the address details. | 20/2/2019
24 |  | Vendor | Speciality | Unable to delete speciality, need alert msg before delete. | 19/2/2019
25 |  | Vendor | Ratings | At front and at admin side if speciality and ratings no available show the msg ' No Ratings Available' Or ' No Speciality Available' should be display same on both side. | 19/2/2019

## Front
Sr. No. | Date | Module | Sub Module | Defect Description | Developers Status | Testers Status |  | Version
1 | 2019-02-06 | Login | Check box | Always checked. It shoulden't be. | 2019-11-02 |  |  | 1
2 |  | Cusine |  | Wrong spelling | 2019-11-02
3 |  | Tags |  | More tags (more than one line) changes the design. | 12/2/2019 (design issue)
4 |  | Add Your Shop and Steps |  | Join the thousands of other restaurants who benefit from having their menus on Sweedesi directory ( Replace restaurants to the 'Sweetmarts' ) same with the steps shown to use the website to the 2nd step. | 2019-11-02 | 2nd step. ( Make it ' Sweetmart Only) | 19/2/2019 | 1
4 |  | Recommended Products |  | Samosa and Peda is available in recommended products though unavailable in admin side. | 2019-11-02
5 |  | Add your shop |  | Should be ' I'm Intrested ' | 2019-11-02 | I Capital | 20/2/2019 | 1
6 |  | Footer |  | Should be 'About Us' instead of 'About us' | 2019-11-02
7 |  | Footer |  | Should be 'Contact Us' instead of 'Contact us' | 2019-11-02
8 |  | Contact Us | Monile number | Mob no tecxt box. Should be 'Mobile No.' instead of 'Mobile No' | 2019-11-02
9 |  | Registration |  | Fb Google Plus not working. | development not done yet
10 | Suggetion | The best food delivery app |  | It can be ' Get it on Google Play' also latest google play symbol should be better for looks
11 | 2019-02-11 | Search Food |  |  | check now (at that time functionality was not done)
12 |  | Favourites |  | Success msg has to be ' Deletted from Wishlist ' | 20/2/2019
13 |  | Existing Products |  | Tool tip for all the products , check skype for code. | 19/2/2019
14 |  | Order Summary |  | Need alert msg before deleting. | 20/2/2019
16 | 2019-02-12 |  | Back to sweedesi Test | When you go back to sweedest Test, payment done success msg shows also redirect to the wrong page. | not understood
17 |  | Login | Login existing user and then disable user from admin>> Go to front then make transaction. | Transaction successful! | 19/2/2019
18 |  | Any sweetmart | Open>> Speciality | If speciality is not available. It shows'No Data Available' Need space before 'No' | 19/2/2019
19 |  | Order Summary | Qty | Qty numbers should be exactly below the Qty column, shift little to the left. | design issue
20 |  | Invoice |  | Rupee symbol needed along with the amount. | 20/2/2019
21 |  | Invoice | Item Total | Make it ' Sub Total ' | 19/2/2019
22 |  | Invoice |  | make it ' Thanks for choosing Sweedesi, Here are your order details: ' | 19/2/2019
23 |  | Invoice |  | Amount should be mention in points. Ex. 160.00 | 20/2/2019
25 |  | Invoice | Grand total | Shift ' Grand Total ' to the right exactly below the ' Delivery Charges ' | 20/2/2019
26 |  | Add your Shop | Sentence has to be>>>>>> | 'Join the thousands of other Sweetmarts who benefit from having their menus on Sweedesi Directory' | 19/2/2019